## Gantt Chart - Manual Duration
Predict pitcher DL based on previous season pitching performance
Task Name | Start Date | End Date | Duration (Days) | Days Complete | Days Remaining | Percent Complete | Start Date in Number Form | 42786 | Use this number for the Minimum Bound of the Horizontal Axis to set the beginning of the chart.
Data Prep: Scrape and parse PitchFx Data | 2017-02-20 | 2017-02-24 | 4 | 4 | 0 | 100%
Data Prep: Aggregate PitchFx Data | 2017-02-24 | 2017-02-28 | 4 | 4 | 0 | 100%
Data Prep: Consolidate Disabled List Data | 2017-02-28 | 2017-03-03 | 3 | 3 | 0 | 100%
Data Prep: Join Datasets to Label | 2017-03-03 | 2017-03-06 | 3 | 3 | 0 | 100%
Exploratory Analysis: Summary | 2017-03-06 | 2017-03-08 | 2 | 2 | 0 | 100%
Exploratory Analysis: Correlation | 2017-03-08 | 2017-03-10 | 2 | 2 | 0 | 100%
Exploratory Analysis: QQ Plot | 2017-03-10 | 2017-03-12 | 2 | 2 | 0 | 100%
Modeling: Creation | 2017-03-12 | 2017-03-17 | 5 | 5 | 0 | 100%
Modeling: Evaluation | 2017-03-17 | 2017-03-22 | 5 | 5 | 0 | 100%
Modeling: Refinement | 2017-03-22 | 2017-04-01 | 10 | 0 | 10 | 0%
Modeling: Prediction for 2017 | 2017-04-01 | 2017-04-02 | 1 | 0.25 | 0.75 | 25%
Draft Report | 2017-04-02 | 2017-04-07 | 5 | 0 | 5 | 0%
Fnal Report | 2017-04-07 | 2017-04-09 | 2 | 0 | 2 | 0%
[7 empty] | Key: | Calculated Cell |  | Manual Entry Cell
[8 empty] | These cells will be automatically calculated based on the inputs on other cells. |  | These cells require manual input so the calculated cells have data to work with.